## Project Data
Project Name | TaskOrbit Conversational Agent
Online team meeting | https://fau.zoom-x.de/j/65288966243?pwd=DnF4jxSAfJugyMmynzjE1BaaFprRbi.1
Production system (if any) | GCP
Test system (if any) | None
GitHub repository | https://github.com/amosproj/amos2026ss04-taskorbit-conversational-agent
GitHub feature board | https://github.com/orgs/amosproj/projects/100/views/2
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/104/views/1
Position of T-shirt logo | Upper Torso Center Large
Link to logo for black T-shirt | https://github.com/amosproj/amos2026ss04-taskorbit-conversational-agent/blob/feature/team-logo-design/Deliverables/sprint-01/team-logo.png
Link to logo for white T-shirt | https://github.com/amosproj/amos2026ss04-taskorbit-conversational-agent/blob/feature/team-logo-design/Deliverables/sprint-01/team-logo.png
Additional materials | https://discord.gg/usXpc5ab
Team maling list | oss-amos-proj4@lists.fau.de

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Fatima | Qiblataina | qiblatainf | qiblatain.fatima@fau.de
Huy | Christoph | Perimora | christoph.huy@campus.tu-berlin.de
Raza | Asad | asadraza17 | asad.raza@fau.de
Jokiel | Rene | BelmontR | rene.jokiel@fau.de
Mosler | Carl | Caerum5 | carl.mosler@tu-berlin.de
Vineesh | Koppay | K-Vineesh | vineesh.koppay@fau.de
Moeez | Abdul | abdulmoeez1225 | abdul.moeez@fau.de
Thakur | Shikhar | shikharthakur2404` | shikhar.thakur@fau.de
Dhruvin | Vekariya | djv03 | dhruvin.vekariya@fau.de
Shameti | Endri | 1Endri | endri.shameti@fau.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
1 | 2026-04-15 |  | Carl | Everyone else | N/A | Rene
2 | 2026-04-22 | Carl | Christoph |  | Endri Shameti | Rene
3 | 2026-04-29 | Christoph | Carl |  | Dhruvin | Rene
4 | 2026-05-06 | Carl | Christoph |  | Qiblatain | Rene
5 | 2026-05-13 | Christoph | Carl |  | Vineesh Koppay | Rene
6 | 2026-05-20 | Carl | Christoph |  | Asad Raza | Rene
7 | 2026-05-27 | Christoph | Carl |  | Abdul Moeez | Rene | Mid-term due
8 | 2026-06-03 | Carl | Christoph |  | Shikhar | Rene
9 | 2026-06-10 | Christoph | Carl |  | Endri Shameti | Rene
10 | 2026-06-17 | Carl | Christoph |  | Dhruvin | Rene
11 | 2026-06-24 | Christoph | Carl |  | Qiblatain | Rene
12 | 2026-07-01 | Carl | Christoph |  | Vineesh Koppay | Rene
13 | 2026-07-08 | Christoph | Carl |  | Abdul Moeez | Rene
14 | 2026-07-15 | Carl | Christoph |  | Asad Raza | Rene | Demo day!
15 | 2026-07-22 | Christoph | Carl |  | Shikhar | Rene | Retrospective
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals | Create a flawless and valuable project that the industry partner will be able to use. Create clean and reusable code and structures
Meeting norms | - be on time -cams on -reach out if you are not gonna make it
- We'll respect each other's opinions and try to communicate as much as possible
Working norms | - Document and comment your code - We'll use branches in a sensefull way and not work directly on the main branch - Transparency - Clear commit messages - We test our code - We write clean code
Coordination norms | - We'll update the feature board in time - If there are multiple devs working on one item, they will communicate and coordinate and not work independently - We balance the workload among the team
Communication norms | - We talk about issues and problems when we face them - Transparent communication - Daily check the corresponding channels
Consideration norms | - We support each other when ever needed - We talk about issues openly - If we can't reach a consensus, we'll vote - We don't take critique personally
Cont. improvement norms | - We'll be open to learn and teach - We encourage critique and improvements efforts
Rewards | - We celebrate milestones with pizza - Very helpful team members get an extra slice of pizza
Sanctions | - Sit ups (at least 10, more if needed)
Signatures
Scrum Master | Rene Jokiel
Product owner | Christoph Huy
Product owner | Carl Mosler
Software developer | Endri Shameti
Software developer | Dhruvin Vekariya
Software developer | Abdul Moeez
Software developer | Vineesh Koppay
Software developer | Asad Raza
Software developer | Qiblatain Fatima
Software developer | Shikhar Thakur

## Product Goal
Product Vision | Project Mission
Product Vision: TaskOrbit provides a domain-independent framework for building reliable conversational AI agents through declarative workflows and structured agent orchestration. The platform enables organizations to create configurable voice and chat agents that integrate STT, LLMs, TTS, and external APIs into unified conversational workflows. By standardizing conversational automation across different business domains, TaskOrbit helps companies reduce manual effort, streamline internal and external processes, and deploy scalable AI-driven assistants without building custom infrastructure from scratch. | The mission of this project is to create an MVP for a Voice AI Agent platform. Within the given project time-frame, the team is committed to delivering a fully functional conversational interface supporting configurable single-agent and multi-agent workflows. Core functionality will include the integration of STT for user input, a LLM backend for conversational processing and reasoning, agent orchestration capabilities, and TTS for audio output. The primary objective of this project is to provide a reliable and extensible end-to-end conversational system through the integration of these core components.

## Product Glossary
Term | Definition
E2E | End-to-End (Workflow): The complete processing pipeline of a system interaction, starting from user input through internal processing and concluding with the system’s resulting output.
LLM (Large Language Model) | The underlying AI backend used for conversational processing, reasoning, and generating text responses based on user prompts
TTS (Text to Speech) | The technology that converts text into a spoken audio output (e.g. the voice of the agent talking to the user)
STT (Speech to Text) | The technology that converts spoken audio input into a text (e.g., transcribing the spoken input from a user for a LLM)
Latency | The time delay between the end of a user's spoken input and the beginning of the agent's audio response (Roundtrip Time)
Agent | An autonomous entity within the platform configured with a specific persona, logic and context to interact with the user via voice (or text)
Agent Orchestration | The capability of the TaskOrbit framework to coordinate multiple specialized conversational agents within a single workflow to solve tasks
Agent Persona | The behavioral guidelines assigned to an agent to ensure it interacts appropriately with the user based on its specific task
Agent Hand-off | The seamless transfer of the conversation from one specialized agent to another when the user's request shifts to a different topic
External Tool | An external integration, API or function invoked by the agent to interact with outside services, databases or systems
Internal Tool | An internal capability, native logic or workflow executed within the agent's system to process information or manage tasks
Conversation | A continuous spoken or written dialogue interaction between a user and an agent, focused on achieving specific tasks
User Interruption | The event where a user starts speaking while agent is actively outputting audio, signaling to stop talking and listen to the new input
Inference Server | The dedicated cloud infrastructure hosting self-hosted, open-source LLMs for TaskOrbit to ensure independent processing
Workflow Engine | The core backend component that manages the state, routing, and execution sequence of complex, multi-step tasks across different agents
Benchmark | A test execution focused primarily on measuring E2E latency across different system configurations to identify the fastest processing variants
Guardrails | Safety and policy constraints implemented within the agent workflow to control and filter LLM outputs, ensuring responses stay within scope
Prerequisite Step | A mandatory preceding agent or task that must be executed or completed before the current agent can be activated
Allowed Handoff | A predefined, permitted path that specifies which other specialized agents the current agent is authorized to transfer the conversation to
Conditional Prerequisite | A dynamic workflow rule where preceding agents are determined on-the-fly based on the routed intent of the user -> overriding static steps

## Sprint Goals
Sprint # | Sprint goal
1 | None
2 | None
3 | None
4 | Optional
5 | Persistent Single-Prompt Agent Prototype
6 | Cloud Deployment/Migration & System Robustness
7 | Advance core platform capabilities & foundation for multi-agent workflow orchestration
8 | Refine agent interaction quality, tool integration & production stability
9 | Conditional Multi-Agent Workflows & Unified Processing
10 | Open-Source Model Integration & Evaluation Framework
11 | System Hardening & Benchmarking
12 | Polishing & Demo Day Prep
13 | Handover & Documentation

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 120 | 120
Sprints
Sprints |  |  |  | Est. remaining |  | Real remaining
1 |  |  | 1 | 120 | 1 | 120
2 |  |  | 16 | 119 | 12 | 119
3 |  |  | 19 | 103 | 18 | 107
4 |  |  | 30 | 84 | 36 | 89
5 |  |  | 29 | 54 | 28 | 53
6 |  |  | 25 | 25 | 21 | 25
Features
1 | None | Design Team Logo #1 | 1 |  | 1
2 | None | Initialize Software Bill of Materials #13 | 3 |  | 2
|  | System Architecture #12 | 5 |  | 5
|  | First UI Design & Implementation #5 | 5 |  | 5
|  | Setup Development Environment #17 | 3 |  | Not Accepted
3 | None | Setup Development Environment #17 | 3 |  | 3
|  | Setup LiveKit Infrastructure #26 | 5 |  | 5
|  | Schema Foundation #6 | 3 |  | 3
|  | Prepare Build Process Review #22 | 3 |  | 2
|  | Core Backend Foundation #7 | 5 |  | 5
4 | Optional | CI/CD Pipeline #10 | 5 |  | 8
|  | Basic Agent Runtime #33 | 5 |  | 5
|  | Basic LLM Integration #18 | 5 |  | 5
|  | DB Integration #32 | 5 |  | 5
|  | Audio Output via LiveKit (Text-to-Speech) # 15 | 5 |  | 5
|  | Audio Input via LiveKit (Speech-to-Text) #14 | 5 |  | 8
5 | Persistent Single-Prompt Agent Prototype | Build Process Video #43 | 2 |  | 3
|  | User Conversation History #45 | 5 |  | Not Accepted
|  | Save Agent Configuration #47 | 3 |  | 3
|  | Load Agent Configuration #51 | 3 |  | 3
|  | Manage Agent Configuration #52 | 3 |  | 3
|  | Logging & Monitoring Setup #11 | 8 |  | 8
|  | Voice Interruption for Audio Chat #55 | 5 |  | 8
6 | Cloud Deployment/Migration & System Robustness | User Conversation History #45 | 5 |  | Not Accepted
|  | User, Design & Build Documentation #74 | 2 |  | 3
|  | Slot Extraction for Structured Task Inputs #70 | 5 |  | 5
|  | Integrate Cloud Environment with IaC #21 | 8 |  | 8
|  | Agent Persona Guardrails #69 | 5 |  | 5
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Velocity Tracking
Sprint # | Story Points Realized | Story Points Estimate
1 | 1 | 1
2 | 12 | 16
3 | 18 | 19
4 | 36 | 30
5 | 28 | 29
6 | 21 | 25
7 | 30 | 30
8 | 18 | 24
9 | 40 | 29
10 | 33 | 31
11 | 32 | 32
12 | 26 | 36
13 |  | 45
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 227 | 227
Sprints
Sprints |  |  |  | Est. remaining |  | Real remaining
7 |  |  | 30 | 227 | 30 | 227
8 |  |  | 24 | 197 | 18 | 197
9 |  |  | 29 | 173 | 40 | 179
10 |  |  | 31 | 144 | 33 | 139
11 |  |  | 32 | 113 | 32 | 106
12 |  |  | 36 | 81 | 26 | 74
13 |  |  | 45 | 45 | 0 | 48
Features
7 | Advance core platform capabilities & foundation for multi-agent workflow orchestration | Agent Config not persistant through text and voice prompts #99 | 3 |  | 3
|  | Agent/LLM Memory Safeguards #56 | 8 |  | 8
|  | Voice input splits into multiple bubbles & numbers/symbols are formatted wrong #102 | 5 |  | 5
|  | Agent Routing Foundation #8 | 8 |  | 8
|  | [PROD] Agent config not loaded correctly #100 | 3 |  | 3
|  | Livekit - Session Limit #112 | 3 |  | 3
8 | Refine agent interaction quality, tool integration & production stability | User Conversation History #45 | 5 |  | 5
|  | Generic Adapter for external Tools #66 | 3 |  | 5
|  | Stream LLM Responses #57 | 5 |  | Not Accepted
|  | [Tools] End Call #116 | 3 |  | 3
|  | Critical Action Confirmation #49 | 3 |  | 5
|  | Microphone Mute interrupts Agent TTS output #101 | 3 |  | Not Accepted
|  | Provider Model Dropdown #87 | 2 |  | Not Accepted
9 | Conditional Multi-Agent Workflows & Unified Processing | Conditional Workflow Engine #71 | 5 |  | 8
|  | [PROD] Grafana Backend Fix #103 | 3 |  | 3
|  | Interchangeable Model Selection #135 | 3 |  | 5
|  | Mute Agent Output #107 | 3 |  | 3
|  | Custom Agent Routing #129 | 5 |  | 8
|  | Stream LLM Responses #57 | 5 |  | 5
|  | Microphone Mute interrupts Agent TTS output #101 | 3 |  | 3
|  | Provider Model Dropdown #87 | 2 |  | 5
10 | Open-Source Model Integration & Evaluation Framework | Cloud Open Source Inference Server #67 | 13 |  | 8
|  | Benchmarking Environment #86 | 8 |  | 8
|  | Investigate high API usage rate #151 | 5 |  | 3
|  | Voice detection does not terminate #153 | 5 |  | 8
|  | Greeting message not showing up in the conversation history #164 | Unplanned critical bug |  | 3
|  | LLM Streaming frontend integration #162 | Unplanned critical bug |  | 3
11 | System Hardening & Benchmarking | Component Benchmarking #68 | 5 |  | Not Accepted
|  | Grafana OS Model Monitoring integration #139 | 8 |  | 8
|  | Self-Hosted LLM Inference on GCP #160 | 8 |  | 13
|  | Email transcription issue #169 | 3 |  | 3
|  | Agent Guadrails need to be added #168 | 8 |  | 5
|  | fix: resolve Gemini intent routing and harden API security #177 | Unplanned critical bug |  | 3
12 | Polishing & Demo Day Prep | Demo Video #187 | 5 |  | Was not presented
|  | UI Clean Up #181 | 8 |  | 8
|  | SBOM Automation & Legal Notices UI #138 | 5 |  | Not Accepted
|  | ElevenLabs and Deepgram provider switching is unreliable #166 | 5 |  | 5
|  | Some LLM providers are not functioning reliably #197 | 5 |  | 5
|  | Allow User to delete History Sessions #191 | 3 |  | 3
|  | Component Benchmarking #68 | 5 |  | Not Accepted
|  | Consistent data extraction from the conversation and showing in history #159 & 183 | Unplanned critical bug |  | 5
13 | Handover & Documentation | Finalize user, (technical) design and build/deploy documentation #182 | 3
|  | Dropdown menu for agent handoffs #203 | 3
|  | Final Repository & Readme Clean up #204 | 5
|  | LiveKit "not configured" in Production #213 | 2
|  | Dynamic Critical Action Confirmation #143 | 3
|  | SBOM Automation & Legal Notices UI #138 | 5
|  | Component Benchmarking #68 | 8
|  | Agent Transfer/Handoff not working #212 | 5
|  | Grafana Backend Logs not displayed correctly #210 | 3
|  | Demo Video #187 | 5
|  | Custom Agents not selectable in Conditional Workflow #214 | 3
Canceled:
Support Markdown formatting in Chat UI #165
Visuals & Fallback for external API Outages #150
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done
General coding standards are met (eg. Formatting, Comments, Logging, no API-Keys in Repo)
Every PR is peer-reviewed by at least one other developer
Documentation is updated (eg. System Architecture, SBOM)
Unit tests for new features have been written
A release candidate representing a functional and verifiable increment over the previous sprint is tagged
Existing features must remain operational and unaffected by the new changes
Sprint release changelog have been written
The system can be built and started from a clean repository checkout
Core workflows are fully integrated and demonstrable end-to-end
All major components are integrated and operational
No critical or blocker defects remain open
Architecture and technical documentation are finalized and updated
SBOM and required project documentation are completed
CI/CD pipeline passes successfully for the release version
Release version is tagged and reproducible
Build and deployment instructions are documented and verified
Source code, documentation, and deliverables are submitted

## Documentation
Type | Link / reference
Team Logo (SVG + PNG) | https://github.com/amosproj/amos2026ss04-taskorbit-conversational-agent/blob/feature/team-logo-design/Deliverables/sprint-01/team-logo.png
Wiki | https://github.com/amosproj/amos2026ss04-taskorbit-conversational-agent/wiki
Repository Documentation | https://github.com/amosproj/amos2026ss04-taskorbit-conversational-agent/tree/main/Documentation
Deliverables | https://github.com/amosproj/amos2026ss04-taskorbit-conversational-agent/tree/main/Deliverables
Readme & Repository | https://github.com/amosproj/amos2026ss04-taskorbit-conversational-agent

## Bill of Materials
# | Context | Name | Version | License | Tool: Syft · deps as of 2026-07-02 (last lockfile change)
1 | npm | @bufbuild/protobuf | 1.10.1 | Apache-2.0 AND BSD-3-Clause
2 | npm | @floating-ui/core | 1.7.5 | MIT
3 | npm | @floating-ui/dom | 1.7.4 | MIT
4 | npm | @floating-ui/dom | 1.7.6 | MIT
5 | npm | @floating-ui/react-dom | 2.1.8 | MIT
6 | npm | @floating-ui/utils | 0.2.11 | MIT
7 | npm | @livekit/components-core | 0.12.13 | Apache-2.0
8 | npm | @livekit/components-react | 2.9.20 | Apache-2.0
9 | npm | @livekit/components-styles | 1.2.0 | Apache-2.0
10 | npm | @livekit/mutex | 1.1.1 | Apache-2.0
11 | npm | @livekit/protocol | 1.45.3 | Apache-2.0
12 | npm | @radix-ui/number | 1.1.1 | MIT
13 | npm | @radix-ui/primitive | 1.1.3 | MIT
14 | npm | @radix-ui/primitive | 1.1.4 | MIT
15 | npm | @radix-ui/react-accessible-icon | 1.1.7 | MIT
16 | npm | @radix-ui/react-accordion | 1.2.12 | MIT
17 | npm | @radix-ui/react-alert-dialog | 1.1.15 | MIT
18 | npm | @radix-ui/react-alert-dialog | 1.1.18 | MIT
19 | npm | @radix-ui/react-arrow | 1.1.7 | MIT
20 | npm | @radix-ui/react-aspect-ratio | 1.1.7 | MIT
21 | npm | @radix-ui/react-avatar | 1.1.10 | MIT
22 | npm | @radix-ui/react-checkbox | 1.3.3 | MIT
23 | npm | @radix-ui/react-collapsible | 1.1.12 | MIT
24 | npm | @radix-ui/react-collection | 1.1.7 | MIT
25 | npm | @radix-ui/react-compose-refs | 1.1.2 | MIT
26 | npm | @radix-ui/react-compose-refs | 1.1.3 | MIT
27 | npm | @radix-ui/react-context | 1.1.2 | MIT
28 | npm | @radix-ui/react-context | 1.1.4 | MIT
29 | npm | @radix-ui/react-context-menu | 2.2.16 | MIT
30 | npm | @radix-ui/react-dialog | 1.1.15 | MIT
31 | npm | @radix-ui/react-dialog | 1.1.18 | MIT
32 | npm | @radix-ui/react-direction | 1.1.1 | MIT
33 | npm | @radix-ui/react-dismissable-layer | 1.1.11 | MIT
34 | npm | @radix-ui/react-dismissable-layer | 1.1.14 | MIT
35 | npm | @radix-ui/react-dropdown-menu | 2.1.16 | MIT
36 | npm | @radix-ui/react-focus-guards | 1.1.3 | MIT
37 | npm | @radix-ui/react-focus-guards | 1.1.4 | MIT
38 | npm | @radix-ui/react-focus-scope | 1.1.11 | MIT
39 | npm | @radix-ui/react-focus-scope | 1.1.7 | MIT
40 | npm | @radix-ui/react-form | 0.1.8 | MIT
41 | npm | @radix-ui/react-hover-card | 1.1.15 | MIT
42 | npm | @radix-ui/react-id | 1.1.1 | MIT
43 | npm | @radix-ui/react-id | 1.1.2 | MIT
44 | npm | @radix-ui/react-label | 2.1.7 | MIT
45 | npm | @radix-ui/react-menu | 2.1.16 | MIT
46 | npm | @radix-ui/react-menubar | 1.1.16 | MIT
47 | npm | @radix-ui/react-navigation-menu | 1.2.14 | MIT
48 | npm | @radix-ui/react-one-time-password-field | 0.1.8 | MIT
49 | npm | @radix-ui/react-password-toggle-field | 0.1.3 | MIT
50 | npm | @radix-ui/react-popover | 1.1.15 | MIT
51 | npm | @radix-ui/react-popper | 1.2.8 | MIT
52 | npm | @radix-ui/react-portal | 1.1.13 | MIT
53 | npm | @radix-ui/react-portal | 1.1.9 | MIT
54 | npm | @radix-ui/react-presence | 1.1.5 | MIT
55 | npm | @radix-ui/react-presence | 1.1.6 | MIT
56 | npm | @radix-ui/react-primitive | 2.1.3 | MIT
57 | npm | @radix-ui/react-primitive | 2.1.7 | MIT
58 | npm | @radix-ui/react-progress | 1.1.7 | MIT
59 | npm | @radix-ui/react-radio-group | 1.3.8 | MIT
60 | npm | @radix-ui/react-roving-focus | 1.1.11 | MIT
61 | npm | @radix-ui/react-scroll-area | 1.2.10 | MIT
62 | npm | @radix-ui/react-select | 2.2.6 | MIT
63 | npm | @radix-ui/react-separator | 1.1.7 | MIT
64 | npm | @radix-ui/react-slider | 1.3.6 | MIT
65 | npm | @radix-ui/react-slot | 1.2.3 | MIT
66 | npm | @radix-ui/react-slot | 1.3.0 | MIT
67 | npm | @radix-ui/react-switch | 1.2.6 | MIT
68 | npm | @radix-ui/react-tabs | 1.1.13 | MIT
69 | npm | @radix-ui/react-toast | 1.2.15 | MIT
70 | npm | @radix-ui/react-toggle | 1.1.10 | MIT
71 | npm | @radix-ui/react-toggle-group | 1.1.11 | MIT
72 | npm | @radix-ui/react-toolbar | 1.1.11 | MIT
73 | npm | @radix-ui/react-tooltip | 1.2.8 | MIT
74 | npm | @radix-ui/react-use-callback-ref | 1.1.1 | MIT
75 | npm | @radix-ui/react-use-callback-ref | 1.1.2 | MIT
76 | npm | @radix-ui/react-use-controllable-state | 1.2.2 | MIT
77 | npm | @radix-ui/react-use-controllable-state | 1.2.3 | MIT
78 | npm | @radix-ui/react-use-effect-event | 0.0.2 | MIT
79 | npm | @radix-ui/react-use-effect-event | 0.0.3 | MIT
80 | npm | @radix-ui/react-use-escape-keydown | 1.1.1 | MIT
81 | npm | @radix-ui/react-use-is-hydrated | 0.1.0 | MIT
82 | npm | @radix-ui/react-use-layout-effect | 1.1.1 | MIT
83 | npm | @radix-ui/react-use-layout-effect | 1.1.2 | MIT
84 | npm | @radix-ui/react-use-previous | 1.1.1 | MIT
85 | npm | @radix-ui/react-use-rect | 1.1.1 | MIT
86 | npm | @radix-ui/react-use-size | 1.1.1 | MIT
87 | npm | @radix-ui/react-visually-hidden | 1.2.3 | MIT
88 | npm | @radix-ui/rect | 1.1.1 | MIT
89 | npm | @types/dom-mediacapture-record | 1.0.22 | MIT
90 | npm | @types/react | 19.2.14 | MIT
91 | npm | @types/react-dom | 19.2.3 | MIT
92 | npm | aria-hidden | 1.2.6 | MIT
93 | npm | class-variance-authority | 0.7.1 | Apache-2.0
94 | npm | clsx | 2.1.1 | MIT
95 | npm | cookie | 1.1.1 | MIT
96 | npm | csstype | 3.2.3 | MIT
97 | npm | detect-node-es | 1.1.0 | MIT
98 | npm | events | 3.3.0 | MIT
99 | npm | get-nonce | 1.0.1 | MIT
100 | npm | jose | 6.2.2 | MIT
101 | npm | livekit-client | 2.18.6 | Apache-2.0
102 | npm | lodash.debounce | 4.0.8 | MIT
103 | npm | loglevel | 1.9.1 | MIT
104 | npm | loglevel | 1.9.2 | MIT
105 | npm | lucide-react | 0.460.0 | ISC
106 | npm | next-themes | 0.4.6 | MIT
107 | npm | radix-ui | 1.4.3 | MIT
108 | npm | react | 19.2.5 | MIT
109 | npm | react-dom | 19.2.5 | MIT
110 | npm | react-remove-scroll | 2.7.2 | MIT
111 | npm | react-remove-scroll-bar | 2.3.8 | MIT
112 | npm | react-router | 7.14.2 | MIT
113 | npm | react-router-dom | 7.14.2 | MIT
114 | npm | react-style-singleton | 2.2.3 | MIT
115 | npm | rxjs | 7.8.2 | Apache-2.0
116 | npm | scheduler | 0.27.0 | MIT
117 | npm | sdp | 3.2.2 | MIT
118 | npm | sdp-transform | 2.15.0 | MIT
119 | npm | set-cookie-parser | 2.7.2 | MIT
120 | npm | sonner | 2.0.7 | MIT
121 | npm | tailwind-merge | 2.6.1 | MIT
122 | npm | taskorbit-frontend | 0.1.0 | UNKNOWN
123 | npm | tslib | 2.8.1 | 0BSD
124 | npm | typed-emitter | 2.1.0 | MIT
125 | npm | use-callback-ref | 1.3.3 | MIT
126 | npm | use-sidecar | 1.1.3 | MIT
127 | npm | use-sync-external-store | 1.6.0 | MIT
128 | npm | usehooks-ts | 3.1.1 | MIT
129 | npm | webrtc-adapter | 9.0.5 | BSD-3-Clause
130 | python | aiofiles | 25.1.0 | UNKNOWN
131 | python | aiohappyeyeballs | 2.6.1 | UNKNOWN
132 | python | aiohttp | 3.13.5 | UNKNOWN
133 | python | aiosignal | 1.4.0 | UNKNOWN
134 | python | aiosqlite | 0.22.1 | UNKNOWN
135 | python | alembic | 1.18.4 | UNKNOWN
136 | python | annotated-doc | 0.0.4 | UNKNOWN
137 | python | annotated-types | 0.7.0 | UNKNOWN
138 | python | anyio | 4.13.0 | UNKNOWN
139 | python | attrs | 26.1.0 | UNKNOWN
140 | python | av | 17.0.1 | UNKNOWN
141 | python | certifi | 2026.4.22 | UNKNOWN
142 | python | cffi | 2.0.0 | UNKNOWN
143 | python | cfgv | 3.5.0 | UNKNOWN
144 | python | charset-normalizer | 3.4.7 | UNKNOWN
145 | python | click | 8.3.3 | UNKNOWN
146 | python | colorama | 0.4.6 | UNKNOWN
147 | python | cryptography | 47.0.0 | UNKNOWN
148 | python | distlib | 0.4.0 | UNKNOWN
149 | python | distro | 1.9.0 | UNKNOWN
150 | python | docstring-parser | 0.18.0 | UNKNOWN
151 | python | eval-type-backport | 0.3.1 | UNKNOWN
152 | python | fastapi | 0.115.14 | UNKNOWN
153 | python | filelock | 3.29.0 | UNKNOWN
154 | python | flatbuffers | 25.12.19 | UNKNOWN
155 | python | frozenlist | 1.8.0 | UNKNOWN
156 | python | google-api-core | 2.30.3 | UNKNOWN
157 | python | google-auth | 2.49.2 | UNKNOWN
158 | python | google-cloud-speech | 2.38.0 | UNKNOWN
159 | python | google-cloud-texttospeech | 2.36.0 | UNKNOWN
160 | python | google-genai | 1.73.1 | UNKNOWN
161 | python | googleapis-common-protos | 1.74.0 | UNKNOWN
162 | python | greenlet | 3.5.1 | UNKNOWN
163 | python | grpcio | 1.80.0 | UNKNOWN
164 | python | grpcio-status | 1.80.0 | UNKNOWN
165 | python | h11 | 0.16.0 | UNKNOWN
166 | python | httpcore | 1.0.9 | UNKNOWN
167 | python | httptools | 0.7.1 | UNKNOWN
168 | python | httpx | 0.28.1 | UNKNOWN
169 | python | identify | 2.6.19 | UNKNOWN
170 | python | idna | 3.13 | UNKNOWN
171 | python | importlib-metadata | 8.7.1 | UNKNOWN
172 | python | iniconfig | 2.3.0 | UNKNOWN
173 | python | jiter | 0.14.0 | UNKNOWN
174 | python | jsonpath-python | 1.1.6 | UNKNOWN
175 | python | jsonschema | 4.26.0 | UNKNOWN
176 | python | jsonschema-specifications | 2025.9.1 | UNKNOWN
177 | python | librt | 0.9.0 | UNKNOWN
178 | python | livekit | 1.1.5 | UNKNOWN
179 | python | livekit-agents | 1.5.6 | UNKNOWN
180 | python | livekit-api | 1.1.0 | UNKNOWN
181 | python | livekit-blingfire | 1.1.0 | UNKNOWN
182 | python | livekit-plugins-deepgram | 1.5.6 | UNKNOWN
183 | python | livekit-plugins-elevenlabs | 1.5.6 | UNKNOWN
184 | python | livekit-plugins-google | 1.5.6 | UNKNOWN
185 | python | livekit-plugins-openai | 1.5.6 | UNKNOWN
186 | python | livekit-plugins-silero | 1.5.6 | UNKNOWN
187 | python | livekit-protocol | 1.1.6 | UNKNOWN
188 | python | mako | 1.3.11 | UNKNOWN
189 | python | markdown-it-py | 4.0.0 | UNKNOWN
190 | python | markupsafe | 3.0.3 | UNKNOWN
191 | python | mdurl | 0.1.2 | UNKNOWN
192 | python | multidict | 6.7.1 | UNKNOWN
193 | python | mypy | 1.20.2 | UNKNOWN
194 | python | mypy-extensions | 1.1.0 | UNKNOWN
195 | python | nest-asyncio | 1.6.0 | UNKNOWN
196 | python | nodeenv | 1.10.0 | UNKNOWN
197 | python | numpy | 2.4.4 | UNKNOWN
198 | python | onnxruntime | 1.25.0 | UNKNOWN
199 | python | openai | 2.32.0 | UNKNOWN
200 | python | openrouter | 0.10.0 | UNKNOWN
201 | python | opentelemetry-api | 1.39.1 | UNKNOWN
202 | python | opentelemetry-exporter-otlp | 1.39.1 | UNKNOWN
203 | python | opentelemetry-exporter-otlp-proto-common | 1.39.1 | UNKNOWN
204 | python | opentelemetry-exporter-otlp-proto-grpc | 1.39.1 | UNKNOWN
205 | python | opentelemetry-exporter-otlp-proto-http | 1.39.1 | UNKNOWN
206 | python | opentelemetry-proto | 1.39.1 | UNKNOWN
207 | python | opentelemetry-sdk | 1.39.1 | UNKNOWN
208 | python | opentelemetry-semantic-conventions | 0.60b1 | UNKNOWN
209 | python | packaging | 26.2 | UNKNOWN
210 | python | pathspec | 1.1.0 | UNKNOWN
211 | python | pillow | 12.2.0 | UNKNOWN
212 | python | platformdirs | 4.9.6 | UNKNOWN
213 | python | pluggy | 1.6.0 | UNKNOWN
214 | python | pre-commit | 4.6.0 | UNKNOWN
215 | python | prometheus-client | 0.22.1 | UNKNOWN
216 | python | prometheus-fastapi-instrumentator | 7.1.0 | UNKNOWN
217 | python | propcache | 0.4.1 | UNKNOWN
218 | python | proto-plus | 1.27.2 | UNKNOWN
219 | python | protobuf | 6.33.6 | UNKNOWN
220 | python | psutil | 7.2.2 | UNKNOWN
221 | python | psycopg | 3.3.3 | UNKNOWN
222 | python | psycopg-binary | 3.3.3 | UNKNOWN
223 | python | pyasn1 | 0.6.3 | UNKNOWN
224 | python | pyasn1-modules | 0.4.2 | UNKNOWN
225 | python | pycparser | 3 | UNKNOWN
226 | python | pydantic | 2.13.3 | UNKNOWN
227 | python | pydantic-core | 2.46.3 | UNKNOWN
228 | python | pydantic-settings | 2.14.0 | UNKNOWN
229 | python | pygments | 2.20.0 | UNKNOWN
230 | python | pyjwt | 2.12.1 | UNKNOWN
231 | python | pytest | 8.4.2 | UNKNOWN
232 | python | pytest-asyncio | 0.24.0 | UNKNOWN
233 | python | python-discovery | 1.2.2 | UNKNOWN
234 | python | python-dotenv | 1.2.2 | UNKNOWN
235 | python | pyyaml | 6.0.3 | UNKNOWN
236 | python | referencing | 0.37.0 | UNKNOWN
237 | python | requests | 2.33.1 | UNKNOWN
238 | python | rich | 15.0.0 | UNKNOWN
239 | python | rpds-py | 0.30.0 | UNKNOWN
240 | python | ruff | 0.7.4 | UNKNOWN
241 | python | shellingham | 1.5.4 | UNKNOWN
242 | python | sniffio | 1.3.1 | UNKNOWN
243 | python | sounddevice | 0.5.5 | UNKNOWN
244 | python | sqlalchemy | 2.0.49 | UNKNOWN
245 | python | starlette | 0.46.2 | UNKNOWN
246 | python | structlog | 24.4.0 | UNKNOWN
247 | python | tenacity | 9.1.4 | UNKNOWN
248 | python | tqdm | 4.67.3 | UNKNOWN
249 | python | typer | 0.25.0 | UNKNOWN
250 | python | types-protobuf | 7.34.1.20260408 | UNKNOWN
251 | python | typing-extensions | 4.15.0 | UNKNOWN
252 | python | typing-inspection | 0.4.2 | UNKNOWN
253 | python | tzdata | 2026.2 | UNKNOWN
254 | python | urllib3 | 2.6.3 | UNKNOWN
255 | python | uvicorn | 0.32.1 | UNKNOWN
256 | python | uvloop | 0.22.1 | UNKNOWN
257 | python | virtualenv | 21.2.4 | UNKNOWN
258 | python | watchfiles | 1.1.1 | UNKNOWN
259 | python | websockets | 15.0.1 | UNKNOWN
260 | python | yarl | 1.23.0 | UNKNOWN
261 | python | zipp | 3.23.1 | UNKNOWN

## Planning Poker
Last Name | First Name | Value
Fatima | Qiblataina |  | #DIV/0! | #DIV/0!
Huy | Christoph
Raza | Asad
Jokiel | Rene
Mosler | Carl |  | 0 | No size
Vineesh | Koppay |  | 1 | Trivial size
Moeez | Abdul |  | 2 | Small size
Thakur | Shikhar |  | 3 | Medium size
Dhruvin | Vekariya |  | 5 | Large size
Shameti | Endri |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value

## Calculations
Sprint # | Story Points Realized | Average Realized (25 SP/s) | Mid Project Release | Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining | Development Speed
1 | 1 | 24.5833
2 | 12 | 24.5833 |  | Release
3 | 18 | 24.5833
4 | 36 | 24.5833 |  | Total |  |  | 120 | 120 |  |  | 20
5 | 28 | 24.5833
6 | 21 | 24.5833 |  | Sprints
7 | 30 | 24.5833 |  | Sprints |  |  |  | Est. remaining |  | Real remaining | Development Speed (≈20 SP/s)
8 | 18 | 24.5833 |  | 1 |  |  | 1 | 120 | 1 | 120 | 120
9 | 40 | 24.5833 |  | 2 |  |  | 16 | 119 | 12 | 119 | 100
10 | 33 | 24.5833 |  | 3 |  |  | 19 | 103 | 18 | 107 | 80
11 | 32 | 24.5833 |  | 4 |  |  | 30 | 84 | 36 | 89 | 60
12 | 26 | 24.5833 |  | 5 |  |  | 29 | 54 | 28 | 53 | 40
13 |  | 24.5833 |  | 6 |  |  | 25 | 25 | 21 | 25 | 20
0
|  |  | Final Release | Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining | Development Speed
Release
|  |  |  | Total |  |  | 227 | 227 |  |  | 32.4286
Sprints
[8 empty] | Est. remaining |  | Real remaining | Development Speed (≈32 SP/s)
|  |  |  | 7 |  |  | 30 | 227 | 30 | 227 | 227
|  |  |  | 8 |  |  | 24 | 197 | 18 | 197 | 194.5714
|  |  |  | 9 |  |  | 29 | 173 | 40 | 179 | 162.1429
|  |  |  | 10 |  |  | 31 | 144 | 33 | 139 | 129.7143
|  |  |  | 11 |  |  | 32 | 113 | 32 | 106 | 97.2857
|  |  |  | 12 |  |  | 36 | 81 | 26 | 74 | 64.8571
|  |  |  | 13 |  |  | 45 | 45 | 0 | 48 | 32.4286

## Bill of Materials (Old) (hidden)
# | Context | Name | Version | License | Comment
1 | python | fastapi | ^0.115.0 | MIT | REST API framework
2 | python | uvicorn | ^0.32.0 | BSD | ASGI server
3 | python | pydantic | ^2.9.0 | MIT | Data validation
4 | python | pydantic-settings | ^2.6.0 | MIT | Settings management
5 | python | python-dotenv | ^1.0.1 | BSD | Environment config
6 | python | livekit-agents | ^1.5.0 | Apache-2.0 | Voice agent framework
7 | python | sqlalchemy | ^2.0.36 | MIT | Database ORM
8 | python | alembic | ^1.14.0 | MIT | Database migrations
9 | python | psycopg | ^3.2.0 | LGPL | PostgreSQL driver
10 | python | structlog | ^24.4.0 | MIT | Structured logging
11 | python | prometheus-fastapi-instrumentator | ^7.0.0 | ISC | FastAPI middleware for Prometheus metrics
12 | python | prometheus-client | ^0.22.0 | Apache-2.0 | Official Prometheus instrumentation client
13 | python | opentelemetry-api | >=1.27.0 | Apache-2.0 | OpenTelemetry tracing and metrics API
14 | python | opentelemetry-sdk | >=1.27.0 | Apache-2.0 | OpenTelemetry reference implementation SDK
15 | python | httpx | ^0.28.1 | BSD | HTTP client
16 | npm | react | ^19.0.0 | MIT | UI framework
17 | npm | react-dom | ^19.0.0 | MIT | React DOM renderer
18 | npm | livekit-client | ^2.5.0 | Apache-2.0 | LiveKit client SDK
19 | npm | @livekit/components-react | ^2.6.0 | Apache-2.0 | LiveKit React components
20 | npm | @livekit/components-styles | ^1.1.0 | Apache-2.0 | LiveKit component styles
21 | npm | react-router-dom | ^7.1.0 | MIT | Client-side routing
22 | npm | sonner | ^2.0.7 | MIT | Toast notifications
23 | npm | next-themes | ^0.4.6 | MIT | Theme management
24 | npm | @radix-ui/react-slot | ^1.1.0 | MIT | Slot component for Radix UI
25 | npm | class-variance-authority | ^0.7.0 | Apache-2.0 | Variant management for classes
26 | npm | clsx | ^2.1.1 | MIT | Class name utility
27 | npm | lucide-react | ^0.460.0 | ISC | Icon library for React
28 | npm | radix-ui | ^1.4.3 | MIT | Radix UI primitives
29 | npm | tailwind-merge | ^2.5.0 | MIT | Tailwind class merging
30 | python | aiosqlite | ^0.22.1 | MIT | Async SQLite driver for testing