## Project Data
Project Name | TaskOrbit Conversational Agent
Online team meeting | https://fau.zoom-x.de/j/65288966243?pwd=DnF4jxSAfJugyMmynzjE1BaaFprRbi.1
Production system (if any) | GCP
Test system (if any) | None
GitHub repository | https://github.com/amosproj/amos2026ss04-taskorbit-conversational-agent
GitHub feature board | https://github.com/orgs/amosproj/projects/100/views/2
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/104/views/1
Position of T-shirt logo | Upper Torso Center Large
Link to logo for black T-shirt | https://github.com/amosproj/amos2026ss04-taskorbit-conversational-agent/blob/feature/team-logo-design/Deliverables/sprint-01/team-logo.png
Link to logo for white T-shirt | https://github.com/amosproj/amos2026ss04-taskorbit-conversational-agent/blob/feature/team-logo-design/Deliverables/sprint-01/team-logo.png
Additional materials | https://discord.gg/usXpc5ab
Team maling list | oss-amos-proj4@lists.fau.de

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Fatima | Qiblatain | qiblatainf | qiblatain.fatima@fau.de
Huy | Christoph | Perimora | christoph.huy@campus.tu-berlin.de
Raza | Asad | asadraza17 | asad.raza@fau.de
Jokiel | Rene | BelmontR | rene.jokiel@fau.de
Mosler | Carl | Caerum5 | carl.mosler@tu-berlin.de
Vineesh | Koppay | K-Vineesh | vineesh.koppay@fau.de
Moeez | Abdul | abdulmoeez1225 | abdul.moeez@fau.de
Thakur | Shikhar | shikharthakur2404` | shikhar.thakur@fau.de
Dhruvin | Vekariya | djv03 | dhruvin.vekariya@fau.de
Shameti | Endri | 1Endri | endri.shameti@fau.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
1 | 2026-04-15 |  | Carl | Everyone else | N/A | Rene
2 | 2026-04-22 | Carl | Christoph |  | Endri Shameti | Rene
3 | 2026-04-29 | Christoph | Carl |  | Dhruvin | Rene
4 | 2026-05-06 | Carl | Christoph |  | Qiblatain | Rene
5 | 2026-05-13 | Christoph | Carl |  | Vineesh Koppay | Rene
6 | 2026-05-20 | Carl | Christoph |  | Asad Raza | Rene
7 | 2026-05-27 | Christoph | Carl |  | Abdul Moeez | Rene | Mid-term due
8 | 2026-06-03 | Carl | Christoph |  | Shikhar | Rene
9 | 2026-06-10 | Christoph | Carl |  | Endri Shameti | Rene
10 | 2026-06-17 | Carl | Christoph |  | Dhruvin | Rene
11 | 2026-06-24 | Christoph | Carl |  | Qiblatain | Rene
12 | 2026-07-01 | Carl | Christoph |  | Vineesh Koppay | Rene
13 | 2026-07-08 | Christoph | Carl |  | Abdul Moeez | Rene
14 | 2026-07-15 | Carl | Christoph |  | Asad Raza | Rene | Demo day!
15 | 2026-07-22 | Christoph | Carl |  | Shikhar | Rene | Retrospective
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals | Create a flawless and valuable project that the industry partner will be able to use. Create clean and reusable code and structures
Meeting norms | - be on time -cams on -reach out if you are not gonna make it
- We'll respect each other's opinions and try to communicate as much as possible
Working norms | - Document and comment your code - We'll use branches in a sensefull way and not work directly on the main branch - Transparency - Clear commit messages - We test our code - We write clean code
Coordination norms | - We'll update the feature board in time - If there are multiple devs working on one item, they will communicate and coordinate and not work independently - We balance the workload among the team
Communication norms | - We talk about issues and problems when we face them - Transparent communication - Daily check the corresponding channels
Consideration norms | - We support each other when ever needed - We talk about issues openly - If we can't reach a consensus, we'll vote - We don't take critique personally
Cont. improvement norms | - We'll be open to learn and teach - We encourage critique and improvements efforts
Rewards | - We celebrate milestones with pizza - Very helpful team members get an extra slice of pizza
Sanctions | - Sit ups (at least 10, more if needed)
Signatures
Scrum Master | Rene Jokiel
Product owner | Christoph Huy
Product owner | Carl Mosler
Software developer | Endri Shameti
Software developer | Dhruvin Vekariya
Software developer | Abdul Moeez
Software developer | Vineesh Koppay
Software developer | Asad Raza
Software developer | Qiblatain Fatima
Software developer | Shikhar Thakur

## Product Goal
Product Vision | Project Mission
Product Vision: TaskOrbit provides a domain-independent framework for building reliable conversational AI agents through declarative workflows and structured agent orchestration. The platform enables organizations to create configurable voice and chat agents that integrate STT, LLMs, TTS, and external APIs into unified conversational workflows. By standardizing conversational automation across different business domains, TaskOrbit helps companies reduce manual effort, streamline internal and external processes, and deploy scalable AI-driven assistants without building custom infrastructure from scratch. | The mission of this project is to create an MVP for a Voice AI Agent platform. Within the given project time-frame, the team is committed to delivering a fully functional conversational interface supporting configurable single-agent and multi-agent workflows. Core functionality will include the integration of STT for user input, a LLM backend for conversational processing and reasoning, agent orchestration capabilities, and TTS for audio output. The primary objective of this project is to provide a reliable and extensible end-to-end conversational system through the integration of these core components.

## Product Glossary
Term | Definition
E2E | End-to-End (Workflow): The complete processing pipeline of a system interaction, starting from user input through internal processing and concluding with the system’s resulting output.
LLM (Large Language Model) | The underlying AI backend used for conversational processing, reasoning, and generating text responses based on user prompts
TTS (Text to Speech) | The technology that converts text into a spoken audio output (e.g. the voice of the agent talking to the user)
STT (Speech to Text) | The technology that converts spoken audio input into a text (e.g., transcribing the spoken input from a user for a LLM)
Latency | The time delay between the end of a user's spoken input and the beginning of the agent's audio response (Roundtrip Time)
Agent | An autonomous entity within the platform configured with a specific persona, logic and context to interact with the user via voice (or text)
Agent Orchestration | The capability of the TaskOrbit framework to coordinate multiple specialized conversational agents within a single workflow to solve tasks
External Tool | An external integration, API or function invoked by the agent to interact with outside services, databases or systems
Internal Tool | An internal capability, native logic or workflow executed within the agent's system to process information or manage tasks
Conversation | A continuous spoken or written dialogue interaction between a user and an agent, focused on achieving specific tasks
User Interruption | The event where a user starts speaking while agent is actively outputting audio, signaling to stop talking and listen to the new input

## Sprint Goals
Sprint # | Sprint goal
1 | None
2 | None
3 | None
4 | Optional
5 | Persistent Single-Prompt Agent Prototype
6 | Cloud Deployment/Migration & System Robustness
7 | Advance core platform capabilities & foundation for multi-agent workflow orchestration
8 | Refine agent interaction quality, tool integration & production stability
9 | Conditional Multi-Agent Workflows, Unified Processing & External Tool Integration
10 | Open-Source Model Integration & Evaluation Framework
11 | System Hardening & Benchmarking
12 | Performance Optimization & Demo Day Prep
13 | Handover & Documentation

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 120 | 120
Sprints
Sprints |  |  |  | Est. remaining |  | Real remaining
1 |  |  | 1 | 120 | 1 | 120
2 |  |  | 16 | 119 | 12 | 119
3 |  |  | 19 | 103 | 18 | 107
4 |  |  | 30 | 84 | 36 | 89
5 |  |  | 29 | 54 | 28 | 53
6 |  |  | 25 | 25 | 21 | 25
Features
1 | None | Design Team Logo #1 | 1 |  | 1
2 | None | Initialize Software Bill of Materials #13 | 3 |  | 2
|  | System Architecture #12 | 5 |  | 5
|  | First UI Design & Implementation #5 | 5 |  | 5
|  | Setup Development Environment #17 | 3 |  | Not Accepted
3 | None | Setup Development Environment #17 | 3 |  | 3
|  | Setup LiveKit Infrastructure #26 | 5 |  | 5
|  | Schema Foundation #6 | 3 |  | 3
|  | Prepare Build Process Review #22 | 3 |  | 2
|  | Core Backend Foundation #7 | 5 |  | 5
4 | Optional | CI/CD Pipeline #10 | 5 |  | 8
|  | Basic Agent Runtime #33 | 5 |  | 5
|  | Basic LLM Integration #18 | 5 |  | 5
|  | DB Integration #32 | 5 |  | 5
|  | Audio Output via LiveKit (Text-to-Speech) # 15 | 5 |  | 5
|  | Audio Input via LiveKit (Speech-to-Text) #14 | 5 |  | 8
5 | Persistent Single-Prompt Agent Prototype | Build Process Video #43 | 2 |  | 3
|  | User Conversation History #45 | 5 |  | Not Accepted
|  | Save Agent Configuration #47 | 3 |  | 3
|  | Load Agent Configuration #51 | 3 |  | 3
|  | Manage Agent Configuration #52 | 3 |  | 3
|  | Logging & Monitoring Setup #11 | 8 |  | 8
|  | Voice Interruption for Audio Chat #55 | 5 |  | 8
6 | Cloud Deployment/Migration & System Robustness | User Conversation History #45 | 5 |  | Not Accepted
|  | User, Design & Build Documentation #74 | 2 |  | 3
|  | Slot Extraction for Structured Task Inputs #70 | 5 |  | 5
|  | Integrate Cloud Environment with IaC #21 | 8 |  | 8
|  | Agent Persona Guardrails #69 | 5 |  | 5
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Velocity Tracking
Sprint # | Story Points Realized | Story Points Estimate
1 | 1 | 1
2 | 12 | 16
3 | 18 | 19
4 | 36 | 30
5 | 28 | 29
6 | 21 | 25
7 | 30 | 30
8 |  | 24
9
10
11
12
13
14
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 167 | 167
Sprints
Sprints |  |  |  | Est. remaining |  | Real remaining
7 |  |  | 30 | 167 | 30 | 167
8 |  |  | 24 | 137 | 0 | 137
9 |  |  | 22 | 113 | 0 | 137
10 |  |  | 26 | 91 | 0 | 137
11 |  |  | 25 | 65 | 0 | 137
12 |  |  | 22 | 40 | 0 | 137
13 |  |  | 18 | 18 | 0 | 137
Features
7 | Advance core platform capabilities & foundation for multi-agent workflow orchestration | Agent Config not persistant through text and voice prompts #99 | 3 |  | 3
|  | Agent/LLM Memory Safeguards #56 | 8 |  | 8
|  | Voice input splits into multiple bubbles & numbers/symbols are formatted wrong #102 | 5 |  | 5
|  | Agent Routing Foundation #8 | 8 |  | 8
|  | [PROD] Agent config not loaded correctly #100 | 3 |  | 3
|  | Livekit - Session Limit #112 | 3 |  | 3
8 | Refine agent interaction quality, tool integration & production stability | User Conversation History #45 | 5
|  | Generic Adapter for external Tools #66 | 3
|  | Stream LLM Responses #57 | 5
|  | [Tools] End Call #116 | 3
|  | Critical Action Confirmation #49 | 3
|  | Microphone Mute interrupts Agent TTS output #101 | 3
|  | Provider Model Dropdown #87 | 2
9 | Conditional Multi-Agent Workflows, Unified Processing & External Tool Integration | Conditional Workflow Engine #71 | 8
|  | [PROD] Grafana Backend Fix #103 | 3
|  | LLM External Tool Execution #44 | 3
|  | Mute Agent Output #107 | 3
|  | Custom Agent Routing #129 | 5
10 | Open-Source Model Integration & Evaluation Framework | Cloud Open Source Inference Server #67 | 8
|  | Benchmarking Environment #86 | 8
|  | Grafana OS Model Monitoring integration | 5
|  | Remove Legacy Text Processing Pipeline #126 | 5
11 | System Hardening & Benchmarking | Component Benchmarking #68 | 8
|  | Benchmark Grafana Integration | 3
|  | Issue with the greeting message | 2
|  | Prevent chat bubble fragmentation during continuous speech | 2
|  | Issue with the text input (not being connected to the worker) | 5
|  | Mutlilanguage Support | 5
12 | Performance Optimization & Demo Day Prep | Final Model Selection | 3
|  | Prepare demo day slide | 3
|  | Create a demo video | 3
|  | Final Model Benchmark | 3
|  | Clean Up UI | 2
|  | Smart Fallback and visualisation if provider is down or usage limit reached | 3
|  | Smart Agent Routing (Latency) | 5
13 | Handover & Documentation | Finalize user, (technical) design and build/deploy documentation | 5
|  | Create project report | 2
|  | Final Bug Fixes | 5
|  | Annotate and clean up Code | 3
|  | Prepare Demoday presentation | 3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done
General coding standards are met (eg. Formatting, Comments, Logging, no API-Keys in Repo)
Every PR is peer-reviewed by at least one other developer
Documentation is updated (eg. System Architecture, SBOM)
Unit tests for new features have been written
A release candidate representing a functional and verifiable increment over the previous sprint is tagged
Existing features must remain operational and unaffected by the new changes
Sprint release changelog have been written
The system can be built and started from a clean repository checkout
Core workflows are fully integrated and demonstrable end-to-end
All major components are integrated and operational
No critical or blocker defects remain open
Architecture and technical documentation are finalized and updated
SBOM and required project documentation are completed
CI/CD pipeline passes successfully for the release version
Release version is tagged and reproducible
Build and deployment instructions are documented and verified
Source code, documentation, and deliverables are submitted

## Documentation
Type | Link / reference
Team Logo (SVG + PNG) | https://github.com/amosproj/amos2026ss04-taskorbit-conversational-agent/blob/feature/team-logo-design/Deliverables/sprint-01/team-logo.png

## Bill of Materials
# | Context | Name | Version | License | Comment
1 | python | fastapi | ^0.115.0 | MIT | REST API framework
2 | python | uvicorn | ^0.32.0 | BSD | ASGI server
3 | python | pydantic | ^2.9.0 | MIT | Data validation
4 | python | pydantic-settings | ^2.6.0 | MIT | Settings management
5 | python | python-dotenv | ^1.0.1 | BSD | Environment config
6 | python | livekit-agents | ^1.5.0 | Apache-2.0 | Voice agent framework
7 | python | sqlalchemy | ^2.0.36 | MIT | Database ORM
8 | python | alembic | ^1.14.0 | MIT | Database migrations
9 | python | psycopg | ^3.2.0 | LGPL | PostgreSQL driver
10 | python | structlog | ^24.4.0 | MIT | Structured logging
11 | python | prometheus-fastapi-instrumentator | ^7.0.0 | ISC | FastAPI middleware for Prometheus metrics
12 | python | prometheus-client | ^0.22.0 | Apache-2.0 | Official Prometheus instrumentation client
13 | python | opentelemetry-api | >=1.27.0 | Apache-2.0 | OpenTelemetry tracing and metrics API
14 | python | opentelemetry-sdk | >=1.27.0 | Apache-2.0 | OpenTelemetry reference implementation SDK
15 | python | httpx | ^0.28.1 | BSD | HTTP client
16 | npm | react | ^19.0.0 | MIT | UI framework
17 | npm | react-dom | ^19.0.0 | MIT | React DOM renderer
18 | npm | livekit-client | ^2.5.0 | Apache-2.0 | LiveKit client SDK
19 | npm | @livekit/components-react | ^2.6.0 | Apache-2.0 | LiveKit React components
20 | npm | @livekit/components-styles | ^1.1.0 | Apache-2.0 | LiveKit component styles
21 | npm | react-router-dom | ^7.1.0 | MIT | Client-side routing
22 | npm | sonner | ^2.0.7 | MIT | Toast notifications
23 | npm | next-themes | ^0.4.6 | MIT | Theme management
24 | npm | @radix-ui/react-slot | ^1.1.0 | MIT | Slot component for Radix UI
25 | npm | class-variance-authority | ^0.7.0 | Apache-2.0 | Variant management for classes
26 | npm | clsx | ^2.1.1 | MIT | Class name utility
27 | npm | lucide-react | ^0.460.0 | ISC | Icon library for React
28 | npm | radix-ui | ^1.4.3 | MIT | Radix UI primitives
29 | npm | tailwind-merge | ^2.5.0 | MIT | Tailwind class merging
30 | python | aiosqlite | ^0.22.1 | MIT | Async SQLite driver for testing

## Planning Poker
Last Name | First Name | Value
Fatima | Qiblatain | 0 | 0 | OK
Huy | Christoph | 0
Raza | Asad
Jokiel | Rene
Mosler | Carl |  | 0 | No size
Vineesh | Koppay |  | 1 | Trivial size
Moeez | Abdul |  | 2 | Small size
Thakur | Shikhar |  | 3 | Medium size
Dhruvin | Vekariya |  | 5 | Large size
|  |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value

## Calculations
Sprint # | Story Points Realized | Average Realized (21 SP/s) | Mid Project Release | Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining | Development Speed
1 | 1 | 20.8571
2 | 12 | 20.8571 |  | Release
3 | 18 | 20.8571
4 | 36 | 20.8571 |  | Total |  |  | 120 | 120 |  |  | 20
5 | 28 | 20.8571
6 | 21 | 20.8571 |  | Sprints
7 | 30 | 20.8571 |  | Sprints |  |  |  | Est. remaining |  | Real remaining | Development Speed (≈20 SP/s)
8 |  | 20.8571 |  | 1 |  |  | 1 | 120 | 1 | 120 | 120
9 |  | 20.8571 |  | 2 |  |  | 16 | 119 | 12 | 119 | 100
10 |  | 20.8571 |  | 3 |  |  | 19 | 103 | 18 | 107 | 80
11 |  | 20.8571 |  | 4 |  |  | 30 | 84 | 36 | 89 | 60
12 |  | 20.8571 |  | 5 |  |  | 29 | 54 | 28 | 53 | 40
13 |  | 20.8571 |  | 6 |  |  | 25 | 25 | 21 | 25 | 20
14 |  | 20.8571 | [8 empty] | 0
|  |  | Final Release | Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining | Development Speed
Release
|  |  |  | Total |  |  | 167 | 167 |  |  | 23.8571
Sprints
[8 empty] | Est. remaining |  | Real remaining | Development Speed (≈24 SP/s)
|  |  |  | 7 |  |  | 30 | 167 | 30 | 167 | 167
|  |  |  | 8 |  |  | 24 | 137 | 0 | 137 | 143.1429
|  |  |  | 9 |  |  | 22 | 113 | 0 | 137 | 119.2857
|  |  |  | 10 |  |  | 26 | 91 | 0 | 137 | 95.4286
|  |  |  | 11 |  |  | 25 | 65 | 0 | 137 | 71.5714
|  |  |  | 12 |  |  | 22 | 40 | 0 | 137 | 47.7143
|  |  |  | 13 |  |  | 18 | 18 | 0 | 137 | 23.8571